## Summary
Survey Builder End To End Regression Test Plan
Owner | David Ellis
Feature
End to end regression test for survey builder
# Survey builder regression plan covering creation of survey with multiple sections, pages, and questions.
# Covers response submission, results review and deletion of survey.
Test Coverage
Key test areas | ScenarioID | Scenarios
Section-based survey organization | S001 | Access Survey Creation Page
Multi-page survey layout | S002 | Create a Survey with Sections, Pages, and Questions
Review submission functionality | S003 | Access Survey via Shared Link
| S004 | Review Survey Responses Before Submission
Anonymous response collection | S005 | Submit Survey Response
Response analytics | S006 | View Survey Response Analytics
| S007 | Delete Survey and Responses
Test Execution Status
Test plan | Not started | Passed | Failed | Total
Release1.0.0 Status | 24 | 0 | 1 | 25

## TestPlan
ScenarioID | Test Case Name | Step Number | Action | Expected Result | Actual Result | Pass/Fail | Comments
S001 | Access Survey Creation Page | 1 | Navigate to homepage as a survey creator | Page displayed
|  | 2 | Select the "Create Assessment" button | "Create Assessment" page is displayed
S002 | Create a Survey with Sections, Pages, and Questions | 1 | Ensure user is on the "Create Assessment" page | Page is open and ready for input
|  | 2 | Enter a survey title: "Regression Test Survey" | Title is accepted
|  | 3 | Add multiple sections to the survey | Sections appear in the survey structure
|  | 4 | Add multiple pages to the survey | Pages are displayed under their respective sections
|  | 5 | Add multiple questions to the survey | Questions are added successfully
|  | 6 | Publish or save the survey | A shareable survey link is generated
|  | 7 | Navigate to "Assessment Templates" page | "Regression Test Survey" appears in the list
S003 | Access Survey via Shared Link | 1 | Confirm "Regression Test Survey" is published | Survey is live
|  | 2 | Navigate to survey link as a survey respondent | Survey completion page opens
S004 | Review Survey Responses Before Submission | 1 | Complete the "Regression Test Survey" with valid answers | User reaches survey submission screen
|  | 2 | Click the "Review Answers" button | "Review your answers" page is displayed
|  | 3 | Confirm answers shown match the ones provided | All answers are accurate and unchanged
|  | 4 | Check "Submit Answers" button is present | Button is present and enabled
S005 | Submit Survey Response | 1 | From the "Review your answers" page | Page loads successfully
|  | 2 | Click the "Submit Answers" button | Confirmation message appears
|  | 3 | Confirm survey completion page is displayed | Page displayed successfully
S006 | View Survey Response Analytics | 1 | Ensure multiple responses have been submitted | Responses exist in the backend
|  | 2 | Navigate to "Assessment Templates" page | Page loads successfully
|  | 3 | View responses for "Regression Test Survey" | Response data is displayed
|  | 4 | Check that response data is anonymous | Data is anonymous
S007 | Delete Survey and Responses | 1 | Navigate to "Assessment Templates" page | Page loads successfully
|  | 2 | Select "Regression Test Survey" | Survey detail page opens
|  | 3 | Click the "Delete" button | Survey and all associated responses are removed from the system

## TestExecutionRelease1.0.0
Tester |  |  | Status
Browser |  |  | Total Number of Tests | 25
|  |  | Not Started | 24
|  |  | Passed | 0
|  |  | Failed | 1
ScenarioID | Scenario | Step | Step Description | Expected Result | Actual Result | Status | Issue ID
S001 | Access Survey Creation Page | 1 | Navigate to homepage as a survey creator | Page displayed |  | Fail
|  | 2 | Select the "Create Assessment" button | "Create Assessment" page is displayed |  | Not started
S002 | Create a Survey with Sections, Pages, and Questions | 1 | Ensure user is on the "Create Assessment" page | Page is open and ready for input |  | Not started
|  | 2 | Enter a survey title: "Regression Test Survey" | Title is accepted |  | Not started
|  | 3 | Add multiple sections to the survey | Sections appear in the survey structure |  | Not started
|  | 4 | Add multiple pages to the survey | Pages are displayed under their respective sections |  | Not started
|  | 5 | Add multiple questions to the survey | Questions are added successfully |  | Not started
|  | 6 | Publish or save the survey | A shareable survey link is generated |  | Not started
|  | 7 | Navigate to "Assessment Templates" page | "Regression Test Survey" appears in the list |  | Not started
S003 | Access Survey via Shared Link | 1 | Confirm "Regression Test Survey" is published | Survey is live |  | Not started
|  | 2 | Navigate to survey link as a survey respondent | Survey completion page opens |  | Not started
S004 | Review Survey Responses Before Submission | 1 | Complete the "Regression Test Survey" with valid answers | User reaches survey submission screen |  | Not started
|  | 2 | Click the "Review Answers" button | "Review your answers" page is displayed |  | Not started
|  | 3 | Confirm answers shown match the ones provided | All answers are accurate and unchanged |  | Not started
|  | 4 | Check "Submit Answers" button is present | Button is present and enabled |  | Not started
S005 | Submit Survey Response | 1 | From the "Review your answers" page | Page loads successfully |  | Not started
|  | 2 | Click the "Submit Answers" button | Confirmation message appears |  | Not started
|  | 3 | Confirm survey completion page is displayed | Page displayed successfully |  | Not started
S006 | View Survey Response Analytics | 1 | Ensure multiple responses have been submitted | Responses exist in the backend |  | Not started
|  | 2 | Navigate to "Assessment Templates" page | Page loads successfully |  | Not started
|  | 3 | View responses for "Regression Test Survey" | Response data is displayed |  | Not started
|  | 4 | Check that response data is anonymous | Data is anonymous |  | Not started
S007 | Delete Survey and Responses | 1 | Navigate to "Assessment Templates" page | Page loads successfully |  | Not started
|  | 2 | Select "Regression Test Survey" | Survey detail page opens |  | Not started
|  | 3 | Click the "Delete" button | Survey and all associated responses are removed from the system |  | Not started